## FishTank Deliverables
GAMES CANADA
LEGO FISHTANK DELIVERABLE CHECKLIST
PRIORITY | OWNER | DELIVERABLE | PLATFORM | OS | MILESTONE/REQ | DEADLINE | UPDATED | STATUS | APPROVAL | EVIDENCE/LOCATION/FEEDBACk
1 | FUNCOM | AI: Fish Behavior and Path-finding | MOBILE | All Devices | Prototyping and Planning | 2013-03-29 | 2013-04-11 | COMPLETE | SUBMITTED | Please see FishTank Prototype Build -> Menu Items: - Fish Movement and Behaviour (AI) - Emotes - Collision (Some AI work for avoiding collision)
1 | FUNCOM | Animation (Tech and Art Prototype) | MOBILE | All Devices | Prototyping and Planning | 2013-03-29 | 2013-04-11 | COMPLETE | SUBMITTED | Please see FishTank Prototype Build -> Menu Items: - Animation 2.0 - Animation Attempts
1 | FUNCOM | Interaction between Objects | MOBILE | All Devices | Prototyping and Planning | 2013-03-29 | 2013-04-11 | COMPLETE | SUBMITTED | Please see FishTank Prototype Build -> Menu Items: - Fish Movement and Behaviour (AI) - Emotes
1 | FUNCOM | Scanning Technical Prototype | MOBILE | All Devices | Prototyping and Planning | 2013-03-29 | 2013-04-11 | COMPLETE | SUBMITTED | Please see FishTank Prototype Build -> Menu Items: - Scanner
1 | FUNCOM | Marketing Video | MOBILE | All Devices | Prototyping and Planning | 2013-03-29 | 2013-04-11 | COMPLETE | SUBMITTED | Delivered Separate from builds
1 | FUNCOM | Personalities Defined (Design Documentation) | MOBILE | All Devices | Prototyping and Planning | 2013-03-29 | 2013-04-11 | ATTENTION | HOLDING | Base documentation is complete. Iteration on Eye and Mouth Decal states and asthetics delaying visual presentation of Fish Personalities. Please see Target Asset Count notes.
1 | FUNCOM | Target Asset Counts | MOBILE | All Devices | Prototyping and Planning | 2013-03-29 | 2013-04-11 | IN PROGRESS | HOLDING | Initial pool of assets requested from LEGO, though due to delays with Eye and Mouth decals Launch target assets were not able to be selected. To resolve LEGO will now only supply 1 frame of Base Eye and Mouth state, and Funcom will take on the remainder work to create all frames and subanimations of this.
1 | FUNCOM | Design Prototypes of Gesture Fish Interactions (GFI) | MOBILE | All Devices | Prototyping and Planning | 2013-03-29 | 2013-05-23 | COMPLETE | SUBMITTED | Please see FishTank Prototype Build -> Menu Items: - Gesture Prototype
| LEGO | Fishtank Environment Direction | MOBILE | All Devices | First Playable | 2013-04-26 | 2013-06-25 | ATTENTION | DECLINED | Over due. Must be locked down imediately.
| LEGO | Fishtank Environment Direction - Background and Plant Life/Details | MOBILE | All Devices | Alpha | 2013-06-25 | 2013-06-25 | COMPLETE | APPROVED | • Background o Sending two files one with plants and one with out. o Locked down awaiting final delivery from Funcom. • Plant Life/Details o Sending some plants that are missing optimizations o Locked down awaiting final delivery from Funcom.
| FUNCOM | Fishtank Environment Asset - Background and Plant Life/Details | MOBILE | All Devices | Alpha | June 28, 2013 | 2013-06-25 | COMPLETE | APPROVED
| LEGO | Fishtank Environment Direction - SandShelves/Levels | MOBILE | All Devices | Alpha | 2013-06-28 | 2013-06-25 | COMPLETE | APPROVED | • Sand Shelves/Levels o No drastic changes o Will build it out of lego o Funcom to make a sand pass over this o LEGO to lock down Friday 28th
| FUNCOM | Fishtank Environment Asset - SandShelves/Levels | MOBILE | All Devices | Alpha | 2013-07-03 | 2013-06-25 | IN PROGRESS |  | With the requested sync up on the 28th instead of the 27th. Max will be unable to deliver till the 3rd of July
| LEGO | Fishtank Environment Direction - Foreground | MOBILE | All Devices | Alpha | 2013-07-02 | 2013-06-25 | IN PROGRESS |  | • Foreground o Lock down Tuesday 02
| LEGO | Fishtank Environment Direction - Build Layer | MOBILE | All Devices | Alpha | 2013-07-02 | 2013-06-25 | IN PROGRESS |  | • Build Layer/Mid Ground o Lock down Tuesday the 02
| LEGO | Fishtank Environment Direction - Corner Pieces | MOBILE | All Devices | Alpha | 2013-07-02 | 2013-06-25 | IN PROGRESS |  | • Corner Piece o Not yet final o Tuesday 02 Deliverable. o Can be mirrored with minor changes.
| LEGO | Fishtank Environment Direction Lock Down | MOBILE | All Devices | Alpha | 2013-07-04 | 2013-06-25 | IN PROGRESS |  | Remaining Direction (Foreground, Build Later and Corner Pieces) locked down
| FUNCOM | Fishtank Environment Lock Down | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-06-25 | IN PROGRESS |  | Remaining Assets locked down and ready for gameplay implementation (Building pass and further optimisation, may not be present in a build on this date)
| LEGO | Sample Music | MOBILE | All Devices | Alpha | TBD | 2013-04-22 | ATTENTION |  | For Funcom to use as a style guide for the tank ambient background music. We will derive from this.
| LEGO | Sample Theme Music, Ambience, Backgorund music, GUI Sounds and Interaction sounds | MOBILE | All Devices | Beta | TBD | 2013-04-22 | ATTENTION |  | Deadline to be refined based on the sample music received previously and what will be required.
| LEGO | Building Insperation Screen Art | MOBILE | All Devices | First Playable | 2013-08-02 | 2013-06-20 | ATTENTION |  | Request to be defiend and addressed.
1 | FUNCOM | Fish Scanning | MOBILE | All Devices | First Playable | 2013-05-17 | 2013-05-23 | COMPLETE | SUBMITTED
| FUNCOM | Sticker Placement (Zero GUI) | MOBILE | All Devices | First Playable | 2013-05-17 | 2013-05-23 | COMPLETE | SUBMITTED
| FUNCOM | Scanned Fish in Tank | MOBILE | All Devices | First Playable | 2013-05-17 | 2013-05-23 | COMPLETE | SUBMITTED
| FUNCOM | Basic Fish Behavior and Communication via Emotes and supporting animations (Fish and Stickers) | MOBILE | All Devices | First Playable | 2013-05-17 | 2013-05-23 | COMPLETE | SUBMITTED
| FUNCOM | Initial Fish Environment running on devices. | MOBILE | All Devices | First Playable | 2013-05-17 | 2013-05-23 | COMPLETE | SUBMITTED
| FUNCOM | User Flow of Scanning “Gamification” (Building Inspiration) | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Object Customisation | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Stickers (Types (Fish, Buildings and Food)) | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Objects into Tank | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Fish Personalities | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Fish tank Environment | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Full Launch Sticker Library | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Full Archetype Fish Mood Animations | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Gesture Fish Interactions | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Localisation System | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Screen flow and GUI | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Launch Sounds and Music | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| FUNCOM | Zero 100% reproducible A Defects | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-04-11 | IN PROGRESS
| LEGO | Localisation Langauges Finalised | MOBILE | All Devices | Beta | 2013-07-05 | 2013-04-22
| LEGO | Final Physical Bricks | MOBILE | All Devices | Beta | 2013-07-05 | 2013-04-22
| LEGO | FishTank Final Logo | MOBILE | All Devices | Beta | 2013-07-05 | 2013-04-22
| LEGO | App Store Icon | MOBILE | All Devices | Beta | 2013-07-05 | 2013-04-22 |  |  | Impacts Marketing Collateral.
| FUNCOM | Deleting Fish (No related activity) | MOBILE | All Devices | Alpha | 2013-07-05 | 2013-05-23 | COMPLETE
| FUNCOM | Zero A, B and C defects | MOBILE | All Devices | Beta | 2013-08-16 | 2013-04-11 | PLANNED
| FUNCOM | Launch Localisation Locked | MOBILE | All Devices | Beta | 2013-08-16 | 2013-04-11 | PLANNED
| FUNCOM | Feature Polish | MOBILE | All Devices | Beta | 2013-08-16 | 2013-04-11 | PLANNED
| FUNCOM | Certification iOS and Android | MOBILE | All Devices | Beta | 2013-08-16 | 2013-04-11 | PLANNED
| FUNCOM | “Go Live” Approval | MOBILE | All Devices | Release | 2013-08-30 | 2013-04-11 | PLANNED
| FUNCOM | Certified Submission - Android | MOBILE | All Devices | Release | 2013-08-30 | 2013-04-11 | PLANNED
| FUNCOM | Certified Submission - iOS | MOBILE | All Devices | Release | 2013-08-30 | 2013-04-11 | PLANNED
| FUNCOM | Marketing Collateral | MOBILE | All Devices | Release | 2013-08-30 | 2013-04-11 | PLANNED
| LEGO | First Playable Playtest Feedback | MOBILE | All Devices | Alpha | Early Alpha | 2013-04-22 |  |  | Funcom will need the Play Test Feedback from the previous phase early in the next phase. Exact date to be clarified with LEGO regarding how soon after a submission a playtest will be performed
| LEGO | Alpha Playtest Feedback | MOBILE | All Devices | Beta | Early Beta | 2013-04-22 |  |  | Funcom will need the Play Test Feedback from the previous phase early in the next phase. Exact date to be clarified with LEGO regarding how soon after a submission a playtest will be performed
| LEGO | Beta Playtest Feedback | MOBILE | All Devices | Release | Early Release | 2013-04-22 |  |  | Funcom will need the Play Test Feedback from the previous phase early in the next phase. Exact date to be clarified with LEGO regarding how soon after a submission a playtest will be performed. Note Feedback would need to be addressed in post release updates based on priority and impact
| LEGO | Hero Creations (For Insperation screens) | MOBILE | All Devices | Beta | June 21, 2013 | 2013-04-12 |  |  | To only use decals and bricks available in the game. Kids must be able to make it. Design to spec numbers and types.
| LEGO | Fish Base Eye and Mouths | MOBILE | All Devices | Prototyping and Planning | TBD | 2013-04-12 | COMPLETE | APPROVED | Sid is working through the base Eyes and Mouths now. We have received 5 of the 10. Tim confirm with Design on the required deadline for this.
| FUNCOM | Random Activities (Events) | MOBILE | All Devices | Post Launch | TBD | 2013-04-12 | TBD
| FUNCOM | On Demand Activities | MOBILE | All Devices | Post Launch | TBD | 2013-04-12 | TBD
| FUNCOM | Progressions (Discussions to be had) o Unlocking Fish Types o Tank Expansion and Unlocking | MOBILE | All Devices | Post Launch | TBD | 2013-04-12 | TBD
| FUNCOM | LEGO ID Integration | MOBILE | All Devices | Post Launch | TBD | 2013-04-12 | TBD
| FUNCOM | Gallery | MOBILE | All Devices | Post Launch | TBD | 2013-04-12 | TBD
| LEGO | Final Box Art and Packaging | MOBILE | All Devices | Marketing | TBD | 2013-04-22
| FUNCOM | Box Art Visuals | MOBILE | All Devices | Marketing | TBD | 2013-05-01 | ATTENTION |  | To Be Revised with new box launch date
| LEGO | Building and Scenery Decals | MOBILE | All Devices |  |  | 2013-04-22 |  |  | To be discussed.

## Elements Deliverables
GAMES CANADA
LEGO ELEMENTS DELIVERABLE CHECKLIST
PRIORITY | OWNER | DELIVERABLE | PLATFORM | OS | MILESTONE/REQUIRED FOR MILESTONE | DEADLINE | UPDATED | STATUS | APPROVAL | EVIDENCE/LOCATION/FEEDBACk
| FUNCOM | World Update Broadcasting Prototype (Multiplayer) | TABLET | All Devices | Multiplayer Proof of Concept | 2012-06-21 | 2013-04-17 | IN PROGRESS
1 | FUNCOM | Procedural World Generation Prototype | TABLET | All Devices | Prototyping and Planning | 2013-06-07 | 2013-06-07 | COMPLETE | SUBMITTED | Loading Build # and beginning a new game. Doing this several times will produce varying world geometry. NOTE: Looking to combine this work with loaded geometry to create more aestically pleasing worlds. Prototype Successful
1 | FUNCOM | Loading and Saving World Prototype | TABLET | All Devices | Prototyping and Planning | 2013-06-07 | 2013-06-07 | COMPLETE | SUBMITTED | Loading Build # and either start a new game or use load game. In the created/loaded world, perform some building and exit. From the menu then use the load game function and load the saved world. Notice the construction is still preserved.
1 | FUNCOM | Brick Placement Prototypes (Ensure the LEGO look and feel) – (See Appendix: Brick Placement/Collection) | TABLET | All Devices | Prototyping and Planning | 2013-06-07 | 2013-06-07 | COMPLETE | SUBMITTED | Load Build ### and enter a new game or load a previous. Along the bottom of the screen is the prototype building menu. Using this interface the user is able to test out Brick placement. LEGO look atained and we are able to get a good direction on Feel.
1 | FUNCOM | Voxel and Special Brick Combination Prototypes (See Appendix: Voxel, Special Bricks) | TABLET | All Devices | Prototyping and Planning | 2013-06-07 | 2013-06-07 | COMPLETE | SUBMITTED | Load Build ### and enter a new game or load a previous. Along the bottom of the screen is the prototype building menu. Using this interface the user is able to test out Brick placement with combination to special bricks.
1 | FUNCOM | Rendering | TABLET | All Devices | Prototyping and Planning | 2013-06-07 | 2013-06-07 | COMPLETE | SUBMITTED | Load Build ### and enter the world. The world is rendering with no visual flaws or errors.
1 | FUNCOM | Water Prototypes | TABLET | All Devices | Prototyping and Planning | 2013-06-07 | 2013-06-07 | COMPLETE | SUBMITTED | Load Build ### and enter a world. Navigate the world to either the edger or the lowerst points. Here you will find our best water prototype implementation. Going under the water will apply initial underwater affects.
1 | FUNCOM | Device Communication Prototype (Multiplayer) | TABLET | All Devices | Prototyping and Planning | 2013-06-07 | 2013-06-07 | COMPLETE | SUBMITTED | Communication has been established in the prototypes though not clearl demonstratedable. This will be further proven out in the Multiplayer proof of concept.
1 | FUNCOM | Blocker Prototype (see Appendix: Blocker) | TABLET | All Devices | Prototyping and Planning | 2013-06-07 | 2013-06-07 | COMPLETE | SUBMITTED | Load Build ### and enter a new game/load previous version. Locate the automatically spawned blockers, they are usually spawned near the players starting location. Alternatively use the debug "Spawn Blocker" button on the interface. Observe their behaviour. Initial roaming and fleeing behaviour to prototype how they will navigate the generated terrain.
| FUNCOM | “Ele” Prototype – Contextual Menu and AI Behavior (See Appendix: ‘Ele’) | TABLET | All Devices | Prototyping and Planning | 2013-06-07 | 2013-06-07 | COMPLETE | SUBMITTED | Load Build ### and enter a new game/load previous version. Locate Ele floating near the player, or alternatively press the "Call Ele" Debug button in the interface. Navigate the world and see how she will follow the player Additionally when near a Monolith (A point of interest) facing it will cause Ele to focus on this for future interactions)
| LEGO | Sample Music | TABLET | All Devices | First Playable | 2013-06-21 | 2013-04-22 |  |  | For Funcom to use as a style guide for the tank ambient background music. We will derive from this.
| LEGO | Colour Pallete and Shape of Digital World Bricks | TABLET | All Devices | Alpha | 2013-08-16 | 2013-04-22
| LEGO | First Pass Physical Bricks | TABLET | All Devices | Alpha | 2013-08-16 | 2013-04-22
| LEGO | Concepts for Tools/Fun Guns | TABLET |  | Alpha | 2013-08-16 | 2013-04-22 |  |  | LDD files prefered, Dependent on Funcom's delivery of "Tool Functionality Concepts"
| FUNCOM | Procedurally Generated World that can be saved on host device | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Collecting Bricks and Building (See Appendix: Brick Placement/Collection) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Scanning and Placing Prefabricated Models (See Appendix: Prefab) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Tool Functionality Concepts | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-22 | PLANNED |  | Not a milestone requirement but a guide to allow LEGO to develop their concepts fo the tool/fungun visuals.
| FUNCOM | Tools (See Appendix: Tools) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Blockers (NPC) – (See Appendix: Blocker) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Collecting Energy (See Appendix: Energy) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Charging and Activating Monoliths for rewards and events | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Monolith Challenges (See Appendix: Monolith) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Events (See Appendix: Event System) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Inventory (See Appendix: Inventory) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | “Ele” Defined (See Appendix: Ele) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Basic Multiplayer | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Mini-game Proposals (Game Design will propose mini-game options that are within scope for launch.) | TABLET | All Devices | First Playable | 2013-08-16 | 2013-04-17 | PLANNED
| FUNCOM | Zero A 100% reproducible defects | TABLET | All Devices | Alpha | 2013-10-11 | 2013-04-17 | PLANNED
| FUNCOM | Full Multiplayer | TABLET | All Devices | Alpha | 2013-10-11 | 2013-04-17 | PLANNED
| FUNCOM | 1x Mini- game (Subject to LEGO approval) | TABLET | All Devices | Alpha | 2013-10-11 | 2013-04-17 | PLANNED
| FUNCOM | Fully Functional UI | TABLET | All Devices | Alpha | 2013-10-11 | 2013-04-17 | PLANNED
| FUNCOM | Launch Blueprints (See Appendix: Blue Prints) | TABLET | All Devices | Alpha | 2013-10-11 | 2013-04-17 | PLANNED
| FUNCOM | Post Launch Feature Proposal | TABLET | All Devices | Alpha | 2013-10-11 | 2013-04-17 | PLANNED
| LEGO | Final Launch Digital Special Bricks | TABLET | All Devices | Beta | 2013-10-11 | 2013-04-22 |  |  | The ones to be present digitally in the game.
| LEGO | Final Ele Concept | TABLET |  | Beta | 2013-10-11 |  |  |  | Preferably in LDD
| LEGO | Final Blocker Concept | TABLET |  | Beta | 2013-10-11 |  |  |  | Preferably in LDD
| LEGO | Final Player Minifigure | TABLET |  | Beta | 2013-10-11
| LEGO | Monolith Designs | TABLET |  | Beta | 2013-10-11 |  |  |  | LDD if possible.
| LEGO | Monolith Challenge Puzzles | TABLET |  | Beta | 2013-10-11
| LEGO | Localisation Langauges Finalised | TABLET | All Devices | Beta | 2013-10-11 | 2013-04-22
| LEGO | Sample Theme Music, Ambience, Backgorund music, GUI Sounds, and Interaction sounds | TABLET | All Devices | Beta | 2013-10-11 | 2013-04-22
| FUNCOM | Zero A, B and C Defects | TABLET | All Devices | Beta | 2013-11-15 | 2013-04-17 | PLANNED
| FUNCOM | No Placeholder Art | TABLET | All Devices | Beta | 2013-11-15 | 2013-04-17 | PLANNED
| FUNCOM | All Prefabricated Models (See Appendix: Blueprints) | TABLET | All Devices | Beta | 2013-11-15 | 2013-04-17 | PLANNED
| FUNCOM | Final Launch GUI | TABLET | All Devices | Beta | 2013-11-15 | 2013-04-17 | PLANNED
| FUNCOM | Launch Sound and Music | TABLET | All Devices | Beta | 2013-11-15 | 2013-04-17 | PLANNED
| FUNCOM | Feature Polish | TABLET | All Devices | Beta | 2013-11-15 | 2013-04-17 | PLANNED
| FUNCOM | Launch Localization Locked - ENG, language - CMA (Proof read) | TABLET | All Devices | Beta | 2013-11-15 | 2013-04-17 | PLANNED
| FUNCOM | “Go Live” Approval | TABLET | All Devices | Release | 2013-12-13 | 2013-04-17 | PLANNED
| FUNCOM | Certification for Target Devices (iOS, Android, Windows) | TABLET | All Devices | Release | 2013-12-13 | 2013-04-17 | PLANNED
| FUNCOM | Marketing Collateral for Social Networks, App Stores, PR, etc. | TABLET | All Devices | Release | 2013-12-13 | 2013-04-17 | PLANNED
| LEGO | First Playable Playtest Feedback | TABLET |  | Alpha | Early Alpha | 2013-04-22
| LEGO | Alpha Playtest Feedback | TABLET |  | Beta | Early Beta | 2013-04-22
| LEGO | Beta Playtest Feedback | TABLET |  | Release | Early Release | 2013-04-22
| LEGO | Launch Blueprint building instructions and Assocaited Rewards | TABLET |  | Beta | October 11, 2013 |  |  |  | Models can be LDD
| LEGO | Final Bricks | TABLET |  | Beta | October 11, 2013
| LEGO | Element Final Logo | TABLET |  | Beta | October 11, 2013
| LEGO | App Store Icon | TABLET |  | Beta | October 11, 2013 |  |  |  | Impacts Marketing Collateral.
| LEGO | Final Box Art and Packaging | TABLET | All Devices | Marketing | TBD | 2013-04-22
| LEGO | LDD Game World | TABLET | All Devices | Prototyping and Planning | TBD | 2013-04-17 | ATTENTION |  | Funcom has requested the game world that was being developed in LDD, so we can evaluate it for visual quality and alternatives. Noted that they will send over the chunks of constructions created so far. Please See LDD World Chunks/Features
| LEGO | LDD World Chunks/Features | TABLET | All Devices | Prototyping and Planning | TBD | 2013-04-17 | ATTENTION |  | LDD World Chunks and Features that are created in the LDD tool. With the request for the game world, LEGO is able to send us what they have so far, being portions of Cliffs, Hills and other geography/constructions.

## FishTank GDD Index
GAMES CANADA
LEGO FishTank GDD INDEX
PRIORITY | DELIVERABLE (YES/NO) | ITEM | DOCUMENT NAME | LOCATION | MILESTONE/REQ (implementation) | DEADLINE | ENTRY UPDATED | STATUS | APPROVAL | Notes
1 |  | Loading Screens | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Transition Screens | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Main Menu | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | User Interface | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Build and Scan | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Building Insperation | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Creation Customisation | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Bring To Life | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Tank Environment Design | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Radial Menu Design | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Emotes (Fish Needs) | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Gesture Interactions | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | AI - Entity Interaction | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | AI - Entity Behaviour | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Deletion | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Data Persistence | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Main Menu | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
1 |  | Building/Scenery Placement | 20130417-First Playable - Feature Document Fish Tank | GitHub Location Pending | First Playable |  | 2013-05-09 | IN PROGRESS | SUBMITTED
2 |  | Customization Version 2 | Raf + Ben to Complete | GitHub Location Pending | ALPHA
2 |  | Scanning Version 2 | Raf + Ben to Complete | GitHub Location Pending | ALPHA
2 |  | Food Functionality | Pending LEGO discussion | GitHub Location Pending | ALPHA
2 |  | Building Functionality | Pending LEGO discussion | GitHub Location Pending | ALPHA
2 |  | Decal System | Pending Karen | GitHub Location Pending | ALPHA
2 |  | Advanced Gesture Interaction | Pending LEGO discussion | GitHub Location Pending | ALPHA
2 |  | UI Sounds | Pending Code | GitHub Location Pending | ALPHA
2 |  | Game Sounds | Pending Code | GitHub Location Pending | ALPHA
2 |  | Music | Pending LEGO discussion | GitHub Location Pending | ALPHA
3 |  | Event System | Pending Management | GitHub Location Pending | Version 2
3 |  | Defensive Buildings | Pending Management | GitHub Location Pending | Version 2
3 |  | Scan Comparison Tech | Pending Management | GitHub Location Pending | Version 2
3 |  | Advanced Food Functionality | Pending Management | GitHub Location Pending | Version 2
3 |  | Progression System | Pending Management | GitHub Location Pending | Version 3
3 |  | Achievements | Pending Management | GitHub Location Pending | Version 3
3 |  | Mini Activity Areas | Pending Management | GitHub Location Pending | Version 3

## Elements GDD Index
GAMES CANADA
LEGO ELEMENTS GDD INDEX
PRIORITY | DELIVERABLE (YES/NO) | ITEM | DOCUMENT NAME | LOCATION | MILESTONE/REQ (implementation) | DEADLINE | ENTRY UPDATED | STATUS | APPROVAL | Notes
1 | YES | Blockers | Blockers.ppt | GitHub Location Pending
1 | YES | BluePrint |  | GitHub Location Pending
1 | YES | Brick Placement |  | GitHub Location Pending
1 | YES | Character Movement |  | GitHub Location Pending
1 | YES | Ele |  | GitHub Location Pending
1 | YES | Energy |  | GitHub Location Pending
1 | YES | Events |  | GitHub Location Pending
1 | YES | Fun Guns |  | GitHub Location Pending
1 | YES | Hybrid World |  | GitHub Location Pending
1 | YES | Inventory |  | GitHub Location Pending
1 | YES | MiniGame |  | GitHub Location Pending
1 | YES | Monolith Challenges |  | GitHub Location Pending
1 | YES | Monolith Charging |  | GitHub Location Pending
1 | YES | Multiplayer |  | GitHub Location Pending
1 | YES | Prefabs |  | GitHub Location Pending
1 |  |  |  | GitHub Location Pending
Note on F3: Tim Dansie: The Milestone where the design will begin implimentation into the game

## Decision Tracker
GAMES CANADA
LEGO ELEMENTS GDD INDEX
PRIORITY | PROJECT | AUTHORITY. | CONCERN/ITEM | DECISION (YES/NO/SPECIFIC) | ENTRY UPDATED | Notes
1 | BRICKIZENS | LEGO | Decided that there will be 3 open slots to create custom worlds. Preset 3 different themes for worlds (Desert, forest, lake). Users have a choice to create 3 of their choice, but any more slots will require a microtransaction. | YES | 2013-06-06
1 | BRICKIZENS | LEGO | The user starts in the middle (x – Crossroad). | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Roads are predefined tile based. The user chooses which they want to place. User Defined. | YES | 2013-06-06
1 | BRICKIZENS | LEGO | World Size – looking at 512x512 square as a starting point. | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Focal points not deletable – Mountains and lakes etc set the environment. | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Premium accounts - Can then have multiple saves | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Premium accounts - Cross device | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Premium accounts - Play with your friends. | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Decided – Cloud saving - No Merging. To problematic and costly for development. | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Decided - If you don’t like where something is placed or want to rebuild it, you have to destroy it. | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Decided - Choose Plots to build. This is the scan plot | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Decided - Only available in god | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Decision – Decorations (city improvements) Place-able in 3rd person placement | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Decided that the player can name their city. | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Decided for | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Social Target - Sending Postcards | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Social Target - Video – Metafile (Record replay(gameplay)/ Mpeg Style) | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Social Target - Gallery (LEGO Curated World) | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Social Target - Gifting Buildings (Potentially a full feature of ELEMENTS system) | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Avata Customisation - Male Female only. (No customization.) | YES | 2013-06-06 | Note: Cards added for some customization but two scoped options. To be defined and planned. Low priority
1 | BRICKIZENS | LEGO | Camera - No First person | YES | 2013-06-06 | 3rd Person and God view only
1 | BRICKIZENS | LEGO | No Maintenance and degradation on the city. | YES | 2013-06-06
1 | BRICKIZENS | LEGO | Unlocks the special static Bricks that feature in the GRID APP | YES | 2013-06-06 | Not things like skateboards etc
1 | BRICKIZENS | LEGO | No Dresses | YES | 2013-06-06
1 | ELEMENTS | LEGO | Elements/sandbox minimum target is Tablet only. | YES | 2013-06-06
1 | ALL | LEGO | Connectivity - All games should function locally, without connectivity. | YES | 2013-06-06

## data
approval | status | priority | scope | platform | OS | Milestone | AUTHORITY | PROJECT | boolean
APPROVED | IN PROGRESS | 0 | SMALL | PC | iOS | Ideation | LEGO | BRICKIZENS | YES
SUBMITTED | PLANNED | 1 | MEDIUM | MOBILE | Android | Prototyping and Planning | FUNCOM | ELEMENTS | NO
DECLINED | ATTENTION | 2 | LARGE | TABLET | Windows | First Playable |  | SANDBOX | TBD
CANCELED | OFF TRACK | 3 | TBD | SOCIAL | All Devices | Multiplayer Proof Of Concept |  | FISHTANK
TBD | COMPLETE |  |  | TBD | Online | Alpha |  | ALL
| PITCH |  |  |  | TBD | Beta
| IN DISCUSSION |  |  |  |  | Release
| IN DESIGN |  |  |  |  | Update 1
| ON HOLD |  |  |  |  | Update 2
| TBD |  |  |  |  | Post Launch
In Review
Complete